## Slide 1: Port Hope Area Initiative –Highland Drive Remediation
REMTECH EAST 2026
April 9, 2026

## Slide 2: Introduction
Ryan Tennant
Project Manager, PMP
rtennant@ecc.net
www.ECC.net
Experience
Over 8 years of experience managing environmental remediation projects across Canada
Expertise executing complex, multi-disciplinary projects
Management of multiple 8 figure remediation and restoration projects.
Role and Responsibilities
ECC’s Project Manager
Onsite single point of contact for CNL
Full authority on all decisions and resource allocations
Ensures execution and compliance with all contract documents and specifications
Maintains overall budget and schedule

## Slide 3: ECC – building a better world
Construction
Environmental
Munitions Response
Disaster Response
$16B
Notes: Briefly on ECC, we're a US based company who's employee owned since 1985.
We manage some of the largest remediation, UXO, Construction and Disaster Response Projects around the globe.
We've been operating in Canada since 2008 managing some of Canada's most challenging remediation projects like the Sydney Tar Ponds, Goose Bay Remediation and now P

## Slide 4: Port Hope Area Initiative (P.H.A.I)
Port Hope Area Initiative (PHAI) was created to clean up historical LLRW with $2.6 billion in Federal funding
LLRW was deposited in various sites in Port Hope from historic waste generated from El Dorado Nuclear (Uranium Refinery) between 1932 and 1988
Program is located in Port Hope Ontario, Canada
1.5 hours E of Toronto / 3 hours SW of Ottawa
ECC currently manages 8 projects
    3 Design Projects
    5 Remediation Projects

## Slide 5
Lions Park
West Beach
Property Remediation & Restoration
Centre Pier
Port Hope Harbour
Highland Dr. Landfill
Chemetron Lagoon
Highland Drive South Ravine
Alexander St. Ravine
Notes: VILIJA

## Slide 6: TEAM engagement
Project execution
Environmental services
Engineering Support
Project management
Radiation Protection
Project Client

## Slide 7: Port hope Highland Drive Sites
3 Separate Highland Drive Projects
Landfill
(2022 - Ongoing)
South Ravine (2024 – 2026)
Tap-On Sites (2025 – 2026)

## Slide 8: Site History
Landfill operated from the 1940s – 1990s accepting municipal solid waste.
LLRW source material was placed within the landfill and used as daily cover.
Groundwater encounters the impacted material and transports contaminants to the adjacent ravine.

## Slide 9: Project Scope
Mobilization & site preparation
Excavation, sorting, and scanning of Municipal Solid Waste (MSW) & Low-Level Radioactive Waste (LLRW)
    Off-site disposal of LLRW
    Re-placement of MSW as backfill
  Remedial verification of excavation extents
  Backfill & clay cap historic landfill
  Site restoration and maintenance
Notes: RYAN
The project’s goal was ultimately to Remove all historic LLRW and bring the Site to a final end use of Residential / Parkland. To-Do this it was broken up into multiple phases.
The short-term objectives started in the Summer of 2023 with the 95% Project Remedial Design Completion and the project planning for mobilization.
In the Fall of 2023, we began remediation of the John St properties to allow for installation of a Portable Water Treatment System and effective remediation of the Coal Gas property.
  Starting with remediation of Arsenic Driven LLRW on the Coal Gas property
  Then installing waterloo barrier type shoring and excavating the deep NAPL material and excavating and backfilling within
  Finally implementing a 1.5 m Risk Management Measure layer (RMM) across the site to allow for approval of a Record of Site Condition change of the property with the Ministry of Environment and Final site restoration
For some subtle foreshadowing, of course that’s exactly how the project ended up going…

## Slide 10: Pre-Mobilization and Concerns
Areas of Major Concern
Proximity to High Traffic Public Areas
Exposing municipal solid waste
Radiological Impacts
    Segregation
    On-site Management

## Slide 11: Highland Drive Landfill Stages
Highland Drive Landfill Stages 1 - 6

## Slide 12: Remedial Concept – Stage 1

## Slide 13: Contamination Control

## Slide 14: Stage 1 Remediation (August 2023)

## Slide 15: Odour Management
Odour Control Foam Cover
Foam Placement

## Slide 16: Remedial Verification

## Slide 17: Stage 2 Remediation (October 2023)

## Slide 18: Stage 3 Remediation (March 2024)
Excavation, sorting, and scanning of MSW and LLRW in Stage 3
MSW placement in Stage 1 of landfill

## Slide 19: MSW Backfill
Placement and Compaction
Layers Placed in 30 cm intervals

## Slide 20: Stage 4 Remediation (July 2024)

## Slide 21: Landfill Findings
Historic Handgun
Replica Hand Grenade

## Slide 22: Stage 5 Floor Remediation (December 2024)
Bulk excavation and loadout
Shipment of up to 120 loads a day!
90% of total volume to LTWMF across all Port Hope Sites

## Slide 23: Stage 5 West Wall Remediation (July 2025)
Excavation on 20m high 2:1 slope!
MSW placement in Stage 3 & 4
Continued excavation into west wall

## Slide 24: Results To Date
Contract Volumes (m3) Compared to Actual Volumes (m3) |  |  |  |  |  |  |  |  | 
Stage | Contract Volume (LLRW) | Contract Volume (MSW) | Total Contract Volume | Actual Volume (LLRW) | Actual Volume (MSW) | Actual Volume (LLRW & MSW) | Percent Volume Change (LLRW & MSW) | Percent Volume Change (LLRW) | Percent Volume Change (MSW)
Stage 1 | 36,000 | 0 | 36,000 | 282,265 | 18,272 | 56,640 | 57.33% | 281.10% | -84.75%
Stage 2 | 14,216 | 0 | 14,216 |  |  | 24,344 | 71.24% |  | 
Stage 3 | 8,900 | 28,600 | 37,500 |  |  | 37,664 | 0.44% |  | 
Stage 4 | 9,000 | 33,000 | 42,000 |  |  | 37,262 | -11.28% |  | 
Stage 5 & 6 | 5,950 | 58,200 | 64,150 |  |  | 144,627 | 125.45% |  | 
Total | 74,066 | 119,800 | 193,866 | 282,265 | 18,272 | 300,537 | 55.02% | 281.10% | -84.75%

## Slide 25: Current & Future Works
Further remediation of Stage 6
Diligent excavation, sorting, scanning and segregating material
Clay capping of entire landfill
Restoration

## Slide 26: Challenges & Lessons Learned
Key Success Factors
Strong Client–Contractor Collaboration Key to Navigating Project Challenges Proactive and Transparent Change Management Timely and Informed Decision-Making
Material Segregation with Comingled LLRW/MSW
Proximity to high use Community infrastructure
Site Characterization/ Contamination Placement ​

## Slide 27
Ryan Tennant
Project manager, PMP
Email: rtennant@ecc.net
www.ECC.net